## Estimation_web
# | Modules | Features | Tasks | UI/UX Total (man-hour) | Frontend (Responsive) (man-hour) | Backend (man-hour) | QA (man-hour) | Total (man-hour) | Total (man-day)
1 | Project initialization, Requirement Analysis, Architecture & System design |  |  | 0 | 2.5 | 15 | 6.5 | 24 | 3
|  | Project Initialization & Repository Setup | Define product vision, naming rationale (TalentTrace AI) & positioning statement | 0 | 0 | 1.25 | 0.25 | 1.5 | 0.1875
|  |  | Initialize GitHub repository with multi-branch strategy (main, develop) | 0 | 0 | 1.25 | 0.25 | 1.5 | 0.1875
|  |  | Configure leak-prevention .gitignore (data & secrets) and .env.example template | 0 | 0 | 1 | 0.5 | 1.5 | 0.1875
|  |  | Set up local development environment, Python 3.10+ workspace, and Docker engine | 0 | 0 | 1 | 0.5 | 1.5 | 0.1875
|  | Requirement Understanding & Clarifications | Review functional features (F1–F6), non-functional constraints, and evaluation rubrics | 0 | 0.5 | 1.5 | 0.75 | 2.75 | 0.34375
|  |  | Compile and document 48 clarification questions, trainer responses, and adopted assumptions | 0 | 0.25 | 1.5 | 1 | 2.75 | 0.34375
|  |  | Map scope boundaries, out-of-scope constraints, and third-party service dependencies | 0 | 0.25 | 1.5 | 0.75 | 2.5 | 0.3125
|  | Architecture & System Design | Design high-level system component diagram, API service boundaries, and data contracts | 0 | 0.5 | 1.5 | 0.5 | 2.5 | 0.3125
|  |  | Design stateful LangGraph topologies with checkpointer state persistence for resumability | 0 | 0.5 | 1.5 | 0.5 | 2.5 | 0.3125
|  |  | Create Risk Register with technical risks, failure modes, likelihood, and mitigation plans | 0 | 0.25 | 1.5 | 0.75 | 2.5 | 0.3125
|  |  | Design relational database schemas and candidate lifecycle state machine | 0 | 0.25 | 1.5 | 0.75 | 2.5 | 0.3125
2 | Environment Foundation, Containerization & Authentication Setup |  |  | 1 | 3.5 | 8.5 | 3 | 16 | 2
|  | Auth & Role-Based Access Control | Initialize FastAPI application with OpenAPI documentation and CORS settings | 0.5 | 0.75 | 1.25 | 0.25 | 2.75 | 0.34375
|  |  | Implement lightweight authentication (Firebase / JWT) supporting Interviewer and Candidate roles | 0.25 | 1 | 1 | 0.5 | 2.75 | 0.34375
|  |  | Implement role-based route middleware to restrict candidates from accessing scoring and rankings | 0.25 | 0.75 | 1.25 | 0.25 | 2.5 | 0.3125
|  | Database Models & Docker Compose | Configure relational schemas for multiple job profiles, candidates, transcripts, and scores | 0 | 0.25 | 1.25 | 0.5 | 2 | 0.25
|  |  | Configure SQLite/Postgres checkpointer for LangGraph state persistence and resumability | 0 | 0.25 | 1.25 | 0.5 | 2 | 0.25
|  |  | Write multi-service Dockerfile and docker-compose.yml with named persistent volumes | 0 | 0.25 | 1.25 | 0.5 | 2 | 0.25
|  |  | Verify single-command startup and volume persistence across container restarts | 0 | 0.25 | 1.25 | 0.5 | 2 | 0.25
3 | Pre-Interview Core: CV Ingestion, OCR, Screening, Candidate Scoring & Social Job Dispatch via MCP (F1, F2) |  |  | 1.5 | 4.5 | 13.5 | 4.5 | 24 | 3
|  | Job Profile Management & LLM Generator | Build UI and API endpoints to create and manage multiple job profiles simultaneously | 0.25 | 0.5 | 0.75 | 0 | 1.5 | 0.1875
|  |  | Implement LLM prompt / chatbot to generate job descriptions and evaluation criteria | 0.25 | 0.5 | 0.5 | 0.25 | 1.5 | 0.1875
|  |  | Configure criteria dimensions (skills, experience, qualifications) with AI-determined default weights | 0 | 0.5 | 0.75 | 0.25 | 1.5 | 0.1875
|  | Social Job Circular Dispatch via MCP (LinkedIn & Twitter/X) | Configure a Model Context Protocol (MCP) client within the Python/LangGraph backend that interfaces with an MCP server (tools) to publish AI-generated job circulars directly to LinkedIn and Twitter (X.com) | 0 | 0.5 | 2.5 | 1 | 4 | 0.5
|  | Dual-Layer Batch CV Parsing & OCR | Build batch CV upload interface supporting 20 sample files (PDF/DOCX) | 0.25 | 0.25 | 0.75 | 0.25 | 1.5 | 0.1875
|  |  | Implement primary text extraction pipeline via PyMuPDF/pdfplumber | 0.25 | 0.25 | 0.75 | 0.25 | 1.5 | 0.1875
|  |  | Implement OCR fallback pipeline (Tesseract/PyMuPDF OCR) for scanned or image-heavy PDFs | 0 | 0.25 | 0.75 | 0.25 | 1.25 | 0.15625
|  |  | Extract structured candidate attributes (contact, education, work history, skills) | 0 | 0.25 | 0.75 | 0.25 | 1.25 | 0.15625
|  | Resumable LangGraph Screening Agent (F1) | Build multi-node LangGraph screening workflow with defined state and transitions | 0 | 0 | 1 | 0.25 | 1.25 | 0.15625
|  |  | Match extracted attributes semantically against requirements (beyond keyword matching) | 0 | 0 | 1 | 0.25 | 1.25 | 0.15625
|  |  | Automatically exclude candidates failing mandatory hard requirements | 0 | 0 | 1 | 0.25 | 1.25 | 0.15625
|  |  | Integrate checkpointer to resume screening automatically after app restart | 0 | 0 | 1 | 0.25 | 1.25 | 0.15625
|  | Scoring Engine (0-100) & Ranking (F2) | Calculate suitability scores on 0–100 scale across skills, experience, and education | 0.25 | 0.25 | 0.5 | 0.25 | 1.25 | 0.15625
|  |  | Compute ATS-style CV–job description match score | 0.25 | 0.25 | 0.5 | 0.25 | 1.25 | 0.15625
|  |  | Generate natural-language score justifications referencing CV evidence | 0 | 0.5 | 0.5 | 0.25 | 1.25 | 0.15625
|  |  | Render ordered candidate ranking dashboard with score breakdowns | 0 | 0.5 | 0.5 | 0.25 | 1.25 | 0.15625
4 | During-Interview Core: Scheduling & 1-on-1 Video Interview (F3) |  |  | 2 | 8.5 | 9.5 | 4 | 24 | 3
|  | Interview Scheduling & Unique Link | Build interview scheduling interface for future date and time selection | 0.25 | 0.5 | 0.75 | 0.25 | 1.75 | 0.21875
|  |  | Generate secure, unique candidate-specific session URLs | 0.25 | 0.5 | 0.75 | 0.25 | 1.75 | 0.21875
|  |  | Link interview session record with candidate ID and active job profile | 0 | 0.5 | 1 | 0 | 1.5 | 0.1875
|  | 1-on-1 WebRTC Call & Reconnection | Implement browser-based 1-on-1 WebRTC video session (Interviewer and Candidate) | 0.5 | 1.25 | 1 | 0.5 | 3.25 | 0.40625
|  |  | Provide in-call media controls (mic mute, camera toggle, disconnect) | 0.5 | 1.25 | 1 | 0.5 | 3.25 | 0.40625
|  |  | Build auto-reconnection logic on brief network disconnection | 0.25 | 1.5 | 0.75 | 0.75 | 3.25 | 0.40625
|  |  | Verify dual-tab operation on localhost for live evaluation demonstration | 0.25 | 1.5 | 0.75 | 0.75 | 3.25 | 0.40625
|  | Dual Audio Capture & Privacy Discard | Capture separate browser audio streams for interviewer and candidate via Web Audio API | 0 | 0.5 | 1.25 | 0.25 | 2 | 0.25
|  |  | Buffer audio chunks in memory/temporary cache for streaming STT processing | 0 | 0.5 | 1.25 | 0.25 | 2 | 0.25
|  |  | Enforce privacy discard rule: purge raw video and audio immediately after transcription | 0 | 0.5 | 1 | 0.5 | 2 | 0.25
5 | During-Interview Core: Real-Time Speech Recognition & Attribution (F4) |  |  | 1 | 3.5 | 8.5 | 3 | 16 | 2
|  | Streaming Speech-to-Text Pipeline | Integrate Google Cloud Speech-to-Text streaming API / Whisper streaming | 0 | 0.5 | 1.5 | 0.5 | 2.5 | 0.3125
|  |  | Stream English audio chunks with minimal perceptible lag during call | 0 | 0.25 | 1.5 | 0.5 | 2.25 | 0.28125
|  |  | Handle silence, overlapping speech, and accented audio without stream failure | 0 | 0.25 | 1.5 | 0.5 | 2.25 | 0.28125
|  | Speaker Attribution & Transcript Storage | Attribute speech turns using participant metadata (Interviewer vs Candidate) without mixed-audio ML diarization | 0.25 | 0.75 | 1 | 0.25 | 2.25 | 0.28125
|  |  | Generate timestamped turns (elapsed interview time or clock time) | 0.25 | 0.75 | 1 | 0.25 | 2.25 | 0.28125
|  |  | Display live scrolling transcript in interview interface | 0.25 | 0.5 | 1 | 0.5 | 2.25 | 0.28125
|  |  | Persist structured transcript to database linked to candidate session | 0.25 | 0.5 | 1 | 0.5 | 2.25 | 0.28125
6 | Post-Interview Core: Q&A Analysis & Consolidated Assessment (F5, F6) |  |  | 2 | 4.5 | 10 | 3.5 | 20 | 2.5
|  | Q&A Segmentation & Small-Talk Filter | Build LangGraph segmentation node to pair interviewer questions with candidate answers | 0.25 | 0.25 | 1.25 | 0.25 | 2 | 0.25
|  |  | Split multi-part interviewer questions into separate evaluation units | 0.25 | 0.25 | 1.25 | 0.25 | 2 | 0.25
|  |  | Filter out greetings, connectivity checks, and casual small-talk from evaluation | 0 | 0.5 | 1 | 0.5 | 2 | 0.25
|  | RAG Technical Accuracy Verification | Integrate RAG pipeline querying authoritative technical documentation to verify technical accuracy | 0.25 | 0.25 | 1 | 0.25 | 1.75 | 0.21875
|  |  | Evaluate candidate answers on relevance, accuracy, completeness, and articulation | 0.25 | 0.25 | 1 | 0.25 | 1.75 | 0.21875
|  |  | Map Q&A pairs to job requirements and highlight unexplored competencies | 0 | 0.25 | 1 | 0.5 | 1.75 | 0.21875
|  |  | Generate evaluation justifications with cited transcript segments | 0 | 0.25 | 1 | 0.5 | 1.75 | 0.21875
|  | Consolidated Assessment & Comparison | Merge CV screening score, ATS match, and interview Q&A analysis into unified 0–100 score | 0.25 | 0.75 | 0.5 | 0.25 | 1.75 | 0.21875
|  |  | Render report with summary of strengths, weaknesses, and evidence gaps | 0.25 | 0.75 | 0.5 | 0.25 | 1.75 | 0.21875
|  |  | Build side-by-side comparison matrix for multiple candidates assessed for the same role | 0.25 | 0.5 | 0.75 | 0.25 | 1.75 | 0.21875
|  |  | Provide exportable / printable formatted report (PDF / styled HTML print) | 0.25 | 0.5 | 0.75 | 0.25 | 1.75 | 0.21875
7 | Creative / Innovation Feature: TalentTrace Dynamic Interviewer Co-Pilot (F11) |  |  | 1 | 3 | 9 | 3 | 16 | 2
|  | Dynamic In-Call Interviewer Co-Pilot | Build background LangGraph agent monitoring live transcript turns against job requirement checklist | 0.25 | 0.75 | 1.5 | 0.5 | 3 | 0.375
|  |  | Dynamically detect unaddressed competencies or shallow candidate responses | 0.25 | 0.75 | 1.5 | 0.5 | 3 | 0.375
|  |  | Generate context-aware follow-up probing questions in real-time on interviewer screen | 0.25 | 0.75 | 1.5 | 0.5 | 3 | 0.375
|  |  | Ensure candidate cannot see the co-pilot assistance (interviewer-only widget) | 0.25 | 0.75 | 1.5 | 0.5 | 3 | 0.375
|  | Innovation Documentation & Rationale | Author 300–500 word justification document covering problem statement, target beneficiary, and value | 0 | 0 | 1.5 | 0.5 | 2 | 0.25
|  |  | Document architectural integration within LangGraph and commit to /docs/innovation_rationale.md | 0 | 0 | 1.5 | 0.5 | 2 | 0.25
8 | System Hardening, Docker Clean Verification & Final Presentation |  |  | 1 | 2.5 | 9.5 | 7 | 20 | 2.5
|  | Privacy Compliance & Data Wipe | Implement backend administrative endpoint DELETE /candidates/{id} for cascading data wipe | 0 | 0.25 | 0.75 | 0.25 | 1.25 | 0.15625
|  |  | Enforce fairness compliance: verify scoring inputs use only job criteria | 0 | 0.25 | 0.75 | 0.25 | 1.25 | 0.15625
|  |  | Document third-party AI service data disclosures in /docs/privacy_note.md | 0 | 0 | 1 | 0.25 | 1.25 | 0.15625
|  |  | Verify structured logging does not expose secrets, credentials, or PII | 0 | 0 | 1 | 0.25 | 1.25 | 0.15625
|  | Batch Throughput & Docker Verification | Benchmark batch screening throughput for 20 sample CVs (<5 minutes target) | 0 | 0.5 | 1.25 | 0.75 | 2.5 | 0.3125
|  |  | Verify single-command startup (docker compose up) on clean machine without cached dependencies | 0 | 0.25 | 1.5 | 0.5 | 2.25 | 0.28125
|  |  | Complete comprehensive README.md with setup commands, architecture, and known limitations | 0 | 0.25 | 1.25 | 0.75 | 2.25 | 0.28125
|  | Tagging, Presentation Deck & Rehearsal | Tag final Git commit as v1.0-final | 0.5 | 0.25 | 0.75 | 1.25 | 2.75 | 0.34375
|  |  | Prepare presentation slide deck with anonymized demo screenshots | 0.25 | 0.5 | 0.5 | 1.5 | 2.75 | 0.34375
|  |  | Rehearse 20–30 minute live demonstration: CV batch screening, 1-on-1 interview call, and assessment | 0.25 | 0.25 | 0.75 | 1.25 | 2.5 | 0.3125
|  |  |  | 9.5 | 32.5 | 83.5 | 34.5 | 160 | 20

## Estimation_mobile (hidden)
# | Modules | Features | Tasks | UI/UX Total (man-day) | Mobile (man-day) | Backend (API) (man-day) | QA (man-day) | Total (man-day)
1 | Project Initialization, Requirement Analysis, Architecture & System Design |  |  | 2 | 5.15 | 0 | 0 | 7.15
|  | Project Initialization, Requirement Analysis, Architecture & System Design | Requirement analysis & documentation (functional + non-functional requirements, stakeholder sign-off) | 1 | 0.25 | 0 | 0 | 1.25
|  |  | Select Framework(Riverpod/Bloc/GetX) and setup | 0 | 0.25 | 0 | 0 | 0.25
|  | Architecture Module | Flutter: Define offline-first architecture (source-of-truth model, sync boundaries) | 0 | 0.25 | 0 | 0 | 0.25
|  |  | Flutter: Define synchronization strategy (delta sync, versioning, conflict policy) | 0 | 0.25 | 0 | 0 | 0.25
|  |  | Flutter: Finalize tech stack, package selection & dependency baseline | 0 | 0.25 | 0 | 0 | 0.25
|  |  | Flutter: repo, DI, routing, environment/flavor config | 0 | 0.5 | 0 | 0 | 0.5
|  |  | Flutter: CI/CD pipeline (build, lint, test, signing) | 0 | 0.25 | 0 | 0 | 0.25
|  |  | Flutter: Build responsive Flutter layouts that automatically adapt content, text, and buttons across phones and tablets. | 0 | 0.25 | 0 | 0 | 0.25
|  | Data design | Backend: Design the main server storage to securely organize and store all system data. | 0 | 0.25 | 0 | 0 | 0.25
|  | API Design | Flutter: Set up secure, structured on-device storage so the app saves data offline and updates smoothly across app versions. | 0 | 0.25 | 0 | 0 | 0.25
|  |  | Flutter: Define RESTful resource URIs, standard HTTP status codes, error payload schemas, and domain-specific error codes. | 0 | 0.9 | 0 | 0 | 0.9
|  |  | Flutter: Generate type-safe DTO models, fromJson/toJson serializers, and immutable data entities for network layers. | 0 | 0.5 | 0 | 0 | 0.5
|  | System Design | Flutter: Design tokens, typography, color & spacing scale | 1 | 0.5 | 0 | 0 | 1.5
|  |  | Flutter: Build reusable atomic UI widgets (CustomButton, AppTextField, StateContainers, Shimmer loaders). | 0 | 0.5 | 0 | 0 | 0.5
2 | Authentication |  |  | 2 | 2.6 | 2 | 2.3393 | 8.9393
|  | Login | UI/UX design: login screen (wireframe + hi-fi mockup) | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: login form UI (input fields, validation, loading/error states) | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Flutter: secure token persistence (secure storage) | 0 | 0.3 | 0 | 0.10633 | 0.40633
|  |  | Backend: authentication API (credential check, JWT token issue) | 0 | 0 | 0.75 | 0.26583 | 1.0158
|  |  | Backend: session/token refresh & expiry handling | 0 | 0 | 0.5 | 0.17722 | 0.67722
|  |  | Flutter: idle auto-logout & session lifecycle | 0 | 0.3 | 0 | 0.10633 | 0.40633
|  | Reset password | UI/UX design – forgot/reset password screen (OTP entry, new password) | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: reset password flow UI (OTP entry, new password, resend timer) | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Backend: OTP generation & verification service (SMS/email) | 0 | 0 | 0.25 | 0.088611 | 0.33861
|  |  | Backend: reset password API | 0 | 0 | 0.5 | 0.17722 | 0.67722
3 | Inspections Dashboard |  |  | 9.1033 | 7.15 | 3.25 | 6.9128 | 26.4161
|  | Home UI | UI/UX: mobile/tablet responsive layout (scrollable cards, grid breakdown) | 2 | 0 | 0 | 0.70888 | 2.7089
|  |  | Flutter: dashboard screen base layout, pull-to-refresh & skeleton loader states | 0 | 0.4 | 0 | 0.14178 | 0.54178
|  | Offline Data show | DB : show the pending aproval data (insert & update) | 0 | 1 | 0 | 0.35444 | 1.3544
|  | Filters | UI/UX : dashboard header & filter bar design (category type, project, date range, refresh) | 2 | 0 | 0 | 0.70888 | 2.7089
|  |  | Flutter: filter bar UI (dropdowns, refresh action) | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  |  | Flutter: filter state management + Hold selected filters, trigger data reload | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Flutter: Send active filters to the API, refresh dashboard cards with results, and manage loading, empty, and error UI states based on the response. | 0 | 0.25 | 0 | 0.088611 | 0.33861
|  |  | Backend — dashboard filter query API (category, project, date range params) | 0 | 0 | 1 | 0.35444 | 1.3544
|  | Charts | UI/UX: chart style design (time-period bar, inspections donut with center total label, status breakdown chart) | 2 | 0 | 0 | 0.70888 | 2.7089
|  |  | Flutter: time-period bar chart widget | 1 | 0.5 | 0 | 0.53166 | 2.0317
|  |  | Flutter: inspections status donut chart widget (center total label) | 0 | 0.6 | 0 | 0.21267 | 0.81267
|  |  | Flutter: status breakdown chart widget | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  |  | Backend: chart aggregation API (time series + status counts) | 0 | 0 | 0.6 | 0.21267 | 0.81267
|  | Stats summary panel | UI/UX: stats summary panel layout (7 stat items — inspections, checklists, notes, pictures, inspectors, projects, resp. parties) | 0.6 | 0 | 0 | 0.21267 | 0.81267
|  |  | Flutter: stats summary panel (inspections, checklists, notes, pictures, inspectors, projects, resp. parties) | 0 | 0.6 | 0 | 0.21267 | 0.81267
|  |  | Backend: stats aggregation API | 0 | 0 | 0.4 | 0.14178 | 0.54178
|  | Breakdown list panels (10 dimensions) | UI/UX: breakdown-list panel design (count, progress bar, A–Z sort icon, download icon, filter icon, "Me" badge highlight) | 1.5 | 0 | 0 | 0.53166 | 2.0317
|  |  | Flutter: reusable breakdown-list component (count, progress bar, sortable A–Z) | 0 | 0.6 | 0 | 0.21267 | 0.81267
|  |  | Flutter: wire up 10 panels (division, project, phase, location, category, checklist, resp. party, inspector type, affiliation, inspector) | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Backend: breakdown aggregation API, 10 dimensions (group-by counts) | 0.0033113 | 0 | 1.25 | 0.44423 | 1.6975
|  |  | Flutter: "Me" badge highlighting for current user's row | 0 | 0.2 | 0 | 0.070888 | 0.27089
4 | Pending Approvals Dashboard |  |  | 3.25 | 5.45 | 3 | 4.147 | 15.847
|  | Header / Filters | UI/UX: review header & filter bar for Pending Approvals labels (reuse existing design, confirm no changes needed) | 0.25 | 0 | 0 | 0.088611 | 0.33861
|  |  | Flutter: wire up Pending Approvals screen (reuse base layout, header & filter bar); manage filter state, call filter API, and bind results to dashboard widgets with loading/empty/error states | 0 | 1.2 | 0 | 0.42533 | 1.6253
|  |  | Backend: pending approvals filter query API (category, project, date range params) | 0 | 0 | 0.75 | 0.26583 | 1.0158
|  | Offline Data show | DB : show the pending aproval data (insert & update) | 0 | 1 | 0 | 0.35444 | 1.3544
|  | Charts | UI/UX: confirm Status and Priority bar chart styling matches existing bar chart component | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: wire Status bar chart widget (reuse bar chart component); call chart aggregation API and bind status counts to the widget, with loading/empty/error states | 0 | 0.6 | 0 | 0.21267 | 0.81267
|  |  | Flutter: wire Priority bar chart widget (reuse bar chart component); bind priority counts from the chart aggregation | 0 | 0.6 | 0 | 0.21267 | 0.81267
|  |  | Backend: chart aggregation API (status counts + priority counts) | 0 | 0 | 0.5 | 0.17722 | 0.67722
|  | Stats summary panel | UI/UX: stats panel layout for Avg. Age (decimal/day value) and Total Risk Factor (numeric score) display styles | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: wire stats summary panel (7 items — approvals, inspections, avg. age, checklists, inspectors, projects, total risk factor); call stats aggregation API and bind values to the panel, with loading/empty/error states | 0 | 0.8 | 0 | 0.28355 | 1.0836
|  |  | Backend: stats aggregation API (incl. avg. age calculation, risk factor sum) | 0 | 0 | 0.5 | 0.17722 | 0.67722
|  | Breakdown list panels (8 dimensions) | UI/UX: confirm breakdown-list panel design covers new dimensions (approver, resp. party/user) and "Me" badge placement | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: wire up 8 panels (project, phase, location, resp. party/user, approver, inspection category, checklist, category) — reuse breakdown-list component; call breakdown aggregation API and bind grouped counts to each panel, with loading/empty/error states | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Backend: breakdown aggregation API, 8 dimensions (group-by counts) | 0 | 0 | 1.25 | 0.44305 | 1.6931
|  |  | Flutter: "Me" badge highlighting on Approver panel (reuse existing badge component) | 0 | 0.25 | 0 | 0.088611 | 0.33861
5 | Start new inspection |  |  | 5 | 6.4 | 5.5 | 5.9901 | 22.8901
|  | Starting a new inspection | UI/UX design dashboard/home screen with "Start new inspection" | 0.5 | 0 | 0 | 0.17722 | 0.67722
|  |  | Flutter: button + navigation to division selection | 0 | 0.3 | 0 | 0.10633 | 0.40633
|  | Selecting division | UI/UX design – division list screen | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: division list UI (loading / empty / error states) | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Backend: GET divisions API | 0 | 0 | 0.75 | 0.26583 | 1.0158
|  |  | Flutter: division selection + local state handling | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Backend/DB : save selected division (insert & update) | 0 | 0 | 0.4 | 0.14178 | 0.54178
|  |  | Flutter: offline caching of division list for offline-first use | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  | Selecting checklist | UI/UX design – checklist list screen | 1.5 | 0 | 0 | 0.53166 | 2.0317
|  |  | Flutter: checklist list UI (search/filter, pagination, loading/empty states) | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Backend: GET checklist list API | 0 | 0 | 1.25 | 0.44305 | 1.6931
|  |  | Backend/DB : insert & update checklist list records | 0 | 0 | 0.4 | 0.14178 | 0.54178
|  |  | UI/UX design – checklist details screen | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: checklist details UI (dynamic form rendering per item type) | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Backend: GET checklist details API | 0 | 0 | 1.25 | 0.44305 | 1.6931
|  |  | Backend/DB : insert & update checklist details records | 0 | 0 | 0.4 | 0.14178 | 0.54178
|  |  | Flutter: offline caching of checklist data (local DB schema, read/write) | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  | Selecting responsible party | UI/UX design – responsible party list screen | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: responsible party list & search UI | 0 | 0.6 | 0 | 0.21267 | 0.81267
|  |  | Backend: GET responsible parties API | 0 | 0 | 0.75 | 0.26583 | 1.0158
|  |  | Flutter: selection logic (single/multi-select) | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  |  | Backend/DB : save responsible party assignment | 0 | 0.25 | 0.3 | 0.19494 | 0.74494
6 | Draft/Temporary Inspection |  |  | 3 | 6.5 | 1.95 | 4.0584 | 15.5084
|  | Filling out the inspection checklist and saving (draft/temporary save) | UI/UX design – draft/recent inspections list screen | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: draft list UI (status badges, sorting, loading/empty states) | 0 | 1.25 | 0 | 0.44305 | 1.6931
|  |  | Backend: GET draft list API | 0 | 0 | 0.5 | 0.17722 | 0.67722
|  |  | Backend/DB : insert & update draft list records | 0 | 0 | 0.4 | 0.14178 | 0.54178
|  |  | UI/UX design – checklist fill-out details screen (pass/fail/NA, comments, attachments) | 2 | 0 | 0 | 0.70888 | 2.7089
|  |  | Flutter: dynamic checklist form rendering + local autosave | 0 | 1.5 | 0 | 0.53166 | 2.0317
|  |  | Flutter: field validation logic (mandatory fields, conditional fields) | 0 | 1.25 | 0 | 0.44305 | 1.6931
|  |  | Backend: save/update draft API | 0 | 0 | 0.6 | 0.21267 | 0.81267
|  |  | Backend/DB : insert & update draft detail records | 0 | 0 | 0.45 | 0.1595 | 0.6095
|  |  | Flutter: offline draft storage (local DB read/write, SQLite/Room) | 0 | 1.5 | 0 | 0.53166 | 2.0317
|  |  | Flutter: View saved/completed inspections | 0 | 1 | 0 | 0.35444 | 1.3544
7 | Synchronization & Sync Control |  |  | 0.6 | 9.75 | 5.25 | 5.5293 | 21.1293
|  | Initial sync | Flutter: first-run sync orchestration (divisions/checklists/parties/inspection & Pending Approval dashboard) | 0 | 1.5 | 0 | 0.53166 | 2.0317
|  |  | Backend: bootstrap sync-down API (versioned master data) | 0 | 0 | 1.25 | 0.44305 | 1.6931
|  | Sync engine (client) | Flutter: offline-first repository interface & abstraction layer | 0 | 1.25 | 0 | 0.44305 | 1.6931
|  |  | Flutter: local write-ahead / pending-changes queue table | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Flutter: outbound delta capture logic (changed-field diffing) | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Flutter: background sync scheduler setup (WorkManager/BGTaskScheduler) | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Flutter: network-state listener & sync trigger logic (periodic + manual) | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Flutter: conflict detection logic (version/timestamp comparison) | 0 | 1.25 | 0 | 0.44305 | 1.6931
|  |  | Flutter: retry & exponential backoff logic | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  |  | Flutter: sync payload serialization & compression | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  | Sync engine (server) | Backend: bulk sync push endpoint (accept batched offline records) | 0 | 0 | 0.75 | 0.26583 | 1.0158
|  |  | Backend: bulk sync pull endpoint (deliver server-side deltas) | 0 | 0 | 1 | 0.35444 | 1.3544
|  |  | Backend: server-side conflict resolution engine (last-write-wins + versioning) | 0 | 0 | 1.25 | 0.44305 | 1.6931
|  |  | Backend: synced-record persistence layer | 0 | 0 | 0.6 | 0.21267 | 0.81267
|  |  | Backend: sync audit trail / change log | 0 | 0 | 0.4 | 0.14178 | 0.54178
|  | Sync UI | UI/UX: sync status screen design (pending/synced/failed states) | 0.6 | 0 | 0 | 0.21267 | 0.81267
|  |  | Flutter: sync status list UI (per-record status rendering) | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Flutter: manual retry control + per-item status indicator | 0 | 0.5 | 0 | 0.17722 | 0.67722
8 | Inspection Details |  |  | 4.05 | 14.5 | 6.55 | 8.8965 | 33.9965
|  | Camera / attach photo | UI/UX : capture UI (shutter control, flash toggle, front/back switch) | 0.5 | 0 | 0 | 0.17722 | 0.67722
|  |  | Flutter: camera plugin integration & platform channel setup | 0 | 1.25 | 0 | 0.44305 | 1.6931
|  |  | Flutter: runtime camera/storage permission handling (Android/iOS) | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Flutter: capture UI (shutter control, flash toggle, front/back switch) | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Flutter: preview & retake screen | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  |  | Flutter: client-side image compression (resize, quality adjustment) | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Backend: photo upload API endpoint | 0 | 0 | 0.3 | 0.10633 | 0.40633
|  |  | Backend: object storage integration (bucket/CDN) + URL generation | 0 | 0 | 0.25 | 0.088611 | 0.33861
|  |  | Backend: photo metadata persistence (timestamp, checkpoint linkage) | 0 | 0 | 0.2 | 0.070888 | 0.27089
|  | Interactive image editing | UI/UX : rotate/crop transforms | 0.25 | 0 | 0 | 0.088611 | 0.33861
|  |  | Flutter: rotate/crop transforms | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Flutter: annotation layer (pen/brush/markers) + persistence | 0 | 1 | 0 | 0.35444 | 1.3544
|  | Attach files | UI/UX : file attachment UI (multi-select, progress indicator) | 1 | 1 | 0 | 0.70888 | 2.7089
|  |  | Flutter: bulk file picker (up to 10 files) + client-side validation (50MB limit) | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Flutter: upload progress UI + retry on failure | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  |  | Flutter – Queue media locally for later upload | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  |  | Backend: bulk file upload API + storage handling | 0 | 0 | 0.75 | 0.26583 | 1.0158
|  |  | Backend: server-side file size/type validation | 0 | 0 | 0.5 | 0.17722 | 0.67722
|  | Attach signature | UI/UX design – signature pad screen | 0.6 | 0 | 0 | 0.21267 | 0.81267
|  |  | Flutter: signature drawing canvas component (draw, clear, save as image) | 0 | 2 | 0 | 0.70888 | 2.7089
|  |  | Backend: signature image upload/save API | 0 | 0 | 0.75 | 0.26583 | 1.0158
|  | Attach from clipboard | Flutter: clipboard read & paste-into-field logic | 0 | 0.75 | 0 | 0.26583 | 1.0158
|  | Duplicate | Flutter: duplicate checkpoint (UI trigger + state clone) | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  |  | Backend: duplicate record creation | 0 | 0 | 0.5 | 0.17722 | 0.67722
|  | Get PDF | UI/UX design : PDF preview/download UI | 0.5 | 0 | 0 | 0.17722 | 0.67722
|  |  | Flutter: PDF generation trigger UI (button, progress/loading state) | 0 | 0.2 | 0 | 0.070888 | 0.27089
|  |  | Flutter: PDF viewer/preview screen integration | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Flutter: native share/export sheet integration | 0 | 0.3 | 0 | 0.10633 | 0.40633
|  |  | Backend: PDF template design & layout engine setup | 0 | 0 | 0.35 | 0.12405 | 0.47405
|  |  | Backend: data-binding service (map checklist data → template fields) | 0 | 0 | 0.35 | 0.12405 | 0.47405
|  |  | Backend: PDF generation service | 0 | 0 | 1 | 0.35444 | 1.3544
|  |  | Backend: PDF object storage integration | 0 | 0 | 0.2 | 0.070888 | 0.27089
|  |  | Backend: A secure system that creates temporary links to download PDF files safely and smoothly. | 0 | 0 | 0.25 | 0.088611 | 0.33861
|  | Mail | UI/UX design : A screen for sending or sharing content where users type the recipient, subject, and message. | 1 | 0 | 0 | 0.35444 | 1.3544
|  |  | Flutter: mail trigger & recipient entry UI | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  |  | Backend: email sending service (attach PDF/report, SMTP/API integration) | 0 | 0 | 0.5 | 0.17722 | 0.67722
|  | Delete | UI/UX design : delete confirmation dialog | 0.2 | 0 | 0 | 0.070888 | 0.27089
|  |  | Flutter: delete confirmation dialog | 0 | 0 | 0 | 0 | 0
|  |  | Backend: soft-delete API + DB update | 0 | 0 | 0.65 | 0.23039 | 0.88039
9 | Notifications |  |  | 1 | 2.5 | 2.5 | 2.1267 | 8.1267
|  | Notification | UI/UX : notification list + unread badge | 1 | 0 | 0 | 0.35444 | 1.3544 | SQA Factor | 0.35444 | 0.35444
|  |  | Flutter: push notification infra (FCM) & token registration | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Flutter: An in-app message center that takes users directly to the right page when tapped. | 0 | 1 | 0 | 0.35444 | 1.3544
|  |  | Backend: notification trigger + dispatch API (push + email) | 0 | 0 | 1.75 | 0.62027 | 2.3703
|  |  | Backend: notification store + read/unread state | 0 | 0 | 0.75 | 0.26583 | 1.0158
|  |  | DB: show offline data (Insert / update / Delete) | 0 | 0.5 | 0 | 0.17722 | 0.67722
|  |  | Total(man-days) | 30.0033 | 60 | 30 | 40 | 160.0033
|  |  | Total(man-months) | 1.5002 | 3 | 1.5 | 2 | 8.0002